Kommit

AI-Powered Bookmark Manager

PROJECT CHARTER & DEVELOPMENT ROADMAP

Version 1.0  •  July 29, 2026

Project: Kommit — AI-Powered Bookmark Manager

Client / Owner:  Keneil Samms

Created: July 29, 2026

Target Launch: September 2026 (8-week timeline)

Status: Phase 0 — Project Kickoff

1. Vision Statement

Kommit is a web-based, AI-powered bookmark manager that lets users save links, receive automatic AI-generated summaries and tags, and retrieve saved content later using natural language search. It transforms passive bookmark hoarding into active knowledge retrieval.

One-liner: Save once. Find by memory.

2. Tech Stack

| Layer | Technology | Rationale |
| --- | --- | --- |
| Backend | Laravel 11+ | Robust PHP framework; queues, events, Scout search built-in |
| Frontend | Inertia.js + Vue 3 | SPA feel without API boilerplate; tight Laravel integration |
| Database | PostgreSQL | pgvector extension for AI embedding search |
| Search | Laravel Scout + Meilisearch | Fast full-text search with typo tolerance |
| AI | Gemini Free version will upgrade later | Summaries, auto-tagging, semantic search embeddings |
| Auth | Laravel Sanctum | Proven auth scaffolding |
| Queue | Laravel Queues + Redis | Background jobs for scraping, AI processing |
| Storage | S3-compatible | Scalable file storage for thumbnails, OG images |
| Testing | Pest PHP + Playwright | Unit/feature/E2E coverage |
| CI/CD | GitHub Actions | Automated tests, linting, deploy |
| Deployment | AWS with Bref | Test and cheap laravel on lambda |

3. Development Phases & Timeline

Phase 1: Requirements & Design (Week 1)

☑ Project Charter (this document)

☐ Product Requirements Document (PRD)

☐ User Stories & Acceptance Criteria

☐ Database Schema Design (ERD)

☐ System Architecture Diagram

☐ Wireframes / Low-fidelity UI mockups

☐ API Contract (if needed for future mobile)

Phase 2: Foundation & Core Infrastructure (Week 2)

☐ Laravel project scaffolding + Inertia + Vue 3

☐ Auth system (register, login, email verification, password reset)

☐ Database migrations & models with relationships

☐ Base layout, navigation, design system (Tailwind)

☐ CI pipeline (GitHub Actions: tests, Pint linting, Larastan)

☐ Dev environment setup docs (README)

Phase 3: Core Features — MVP (Weeks 3–4)

☐ Link CRUD (save, edit, delete, archive)

☐ URL metadata extraction (title, description, OG image, favicon)

☐ Manual tagging and categorization (collections/folders)

☐ Dashboard with saved links grid/list view

☐ Basic search (title, URL, description full-text)

☐ Import bookmarks (Chrome/Firefox HTML export)

Phase 4: AI Features (Weeks 5–6)

☐ AI auto-summarization on link save (queued job)

☐ AI auto-tagging based on page content

☐ Semantic search with embeddings (pgvector)

☐ "Ask your vault" — natural language query interface

☐ Smart suggestions ("You saved similar links about...")

Phase 5: Polish & Power Features (Week 7)

☐ Browser extension (Chrome — save with one click)

☐ Public/private collections with shareable URLs

☐ Bulk actions (multi-select, bulk tag, bulk delete)

☐ Reading list / "Read Later" queue

☐ Favorites and pinned links

☐ Dark mode

☐ Responsive mobile design

Phase 6: Quality & Launch (Week 8)

☐ Comprehensive test suite (unit, feature, E2E)

☐ Performance audit (N+1 queries, caching, lazy loading)

☐ Security audit (CSRF, XSS, rate limiting, input validation)

☐ Accessibility audit (WCAG 2.1 AA)

☐ SEO & Open Graph for public collections

☐ Production deployment

☐ Monitoring & error tracking (Sentry, Laravel Pulse)

☐ Launch checklist sign-off

4. Core Feature Set (MVP Scope)

Must Have (P0) — Ship-blocking

[P0] User authentication (register, login, logout, password reset)

[P0] Save a link (paste URL → auto-extract metadata)

[P0] View saved links (grid + list view with thumbnails)

[P0] Organize into collections/folders

[P0] Manual tags

[P0] Full-text search

[P0] AI auto-summary on save

[P0] AI auto-tags on save

[P0] Delete / archive links

Should Have (P1) — Launch with if possible

[P1] Natural language search ("that React article from last week")

[P1] Import bookmarks from browser

[P1] Public shareable collections

[P1] Bulk operations

[P1] Favorites / pins

[P1] Dark mode

Nice to Have (P2) — Post-launch

[P2] Browser extension

[P2] "Ask your vault" conversational AI

[P2] Smart duplicate detection

[P2] Reading time estimates

[P2] RSS feed monitoring

[P2] Team/shared vaults

[P2] API for third-party integrations

5. Non-Functional Requirements

| Category | Requirement |
| --- | --- |
| Performance | Dash board loads in < 2s; search results in < 500ms |
| Scalability | Support 10K+ links per user without degradation |
| Security | OWASP Top 10 compliance; encrypted API keys at rest |
| Availability | 99.5% uptime target |
| Code Quality | 80%+ test coverage; zero Larastan level-6 errors |
| Accessibility | WCAG 2.1 AA compliance |
| Browser Support | Chrome, Firefox, Safari, Edge (latest 2 versions) |

6. Risks & Mitigations

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| AI API costs spiral | High | Medium | Cache summaries; rate-limit AI calls per user; batch processing |
| Scraping blocked by sites | Medium | High | Fallback to OG meta tags; graceful degradation |
| Scope creep | High | High | Strict P0/P1/P2 prioritization; weekly scope review |
| pgvector learning curve | Medium | Medium | Start with Meilisearch; add vector search incrementally |
| Solo developer burnout | High | Medium | Time-boxed sprints; cut P2 ruthlessly |

7. Definition of Done (DoD)

A feature is considered "done" when all of the following conditions are met:

☐ Code is written and follows project coding standards

☐ Unit tests pass with adequate coverage

☐ Feature tests cover the happy path + key edge cases

☐ Code passes Larastan (level 6) with zero errors

☐ Code passes Laravel Pint with zero violations

☐ Manually tested in browser (desktop + mobile viewport)

☐ Reviewed against acceptance criteria in the user story

☐ No console errors or warnings

☐ Documented (PHPDoc on public methods; README updated if needed)

8. Coding Standards

| Area | Standard |
| --- | --- |
| PHP | PSR-12 via Laravel Pint |
| Vue | Composition API + <script setup> syntax |
| CSS | Tailwind utility-first; extract components for repeated patterns |
| Git | Conventional commits (feat:, fix:, refactor:, test:, docs:) |
| Branching | main (production) → develop (integration) → feature/* branches |
| PRs | Self-review checklist before merge; no direct pushes to main |

This is a living document. Update the status check-boxes as we progress through each phase.